## PA_August_2018
Priority | Issue ID | Summary | Status
3-Low | #71632 | Simplify the way of creating timesheets each month | Pending
3-Low | #71639 | Indicate the dates of the weeks and match them to the calendar | Pending
3-Low | #71627 | Email sending to users directly from OLTS | Pending
3-Low | #72558 | Add the button "Clear" at the new option admin log as user | Pending
3-Low | #72528 | Email address not recognized by the system | Pending
Defects Reported by Business August 18
Priority | Issue ID | Summary | Status
|  | Notification service workflow analysis | Pending
|  | Procedures optimization | Pending

## DSR_August_2018
Daily Status Report -- August 2018
Name | Deepak Gogia | Manager | Mr. Ravi Singh | Client Name | Hays Business Solution
Employee ID | 1537513 | Email ID | ravi5.s@tcs.com | Location | Noida
Role | Developer | Contact No | 7668401200 | Email ID | deepak.gogia@hays.com
Contact No | 9643439385
Srno | Date | Task | Project | Effort Hrs | Status | Remarks
1 | 2018-08-01 | Timesheet Status is blank in Find Job Page for admin [ Create scenerio] | OLTS Application | 3 | InProgress | timesheet status is not empty for contractor
2 | 2018-08-01 | Timesheet Status is blank in Find Job Page for admin [ Change in Database Script ] | OLTS Application | 5 | Completed
3 | 2018-08-02 | Notification service workflow analysis | OLTS WinService | 2 | InProgress
4 | 2018-08-02 | Access for Consultant/Super Admin/Admin to View Timesheet [ Analysis current flow] | OLTS Application | 1 | Completed
5 | 2018-08-02 | Access for Consultant/Super Admin/Admin to View Timesheet [ Replicate at PRE-PROD environment and development end] | OLTS Application | 1 | Completed
6 | 2018-08-02 | Access for Consultant/Super Admin/Admin to View Timesheet [ Change code] | OLTS Application | 3 | Completed
7 | 2018-08-02 | Access for Consultant/Super Admin/Admin to View Timesheet [ Testing] | OLTS Application | 1 | InProgress
8 | 2018-08-03 | Access for Consultant/Super Admin/Admin to View Timesheet [ Testing] | OLTS Application | 2 | Completed
9 | 2018-08-03 | Delete timesheet data from database as reported by Business | OLTS Application | 1 | Completed
10 | 2018-08-03 | Notification service workflow analysis | OLTS WinService | 5 | InProgress
11 | 2018-08-06 | Notification service workflow analysis | OLTS WinService | 5 | InProgress
12 | 2018-08-06 | Validate Email address [Change code for validate the email address with Regular Expression] | OLTS Application | 2 | Completed
13 | 2018-08-06 | Validate Email address [Testing] | OLTS Application | 1 | Completed
14 | 2018-08-07 | Onleave
15 | 2018-08-09 | Test Application on PRE-PROD environment | OLTS Application | 2 | Completed
16 | 2018-08-09 | Test Application on PROD environment | OLTS Application | 2 | Completed
17 | 2018-08-09 | Replicate PROD issue on PRE-PROD environment[ Timesheet open] | OLTS Application | 1 | Completed
18 | 2018-08-09 | Replicate PROD issue on PRE-PROD environment[ Timesheet open- Change code] | OLTS Application | 3 | Completed
19 | 2018-08-10 | Analysis Error and find its solution | OLTS Application | 8
20 | 2018-08-13 | INC000007415989 has been submitted. FR OLTS / Contractor cannot reach timesheets [ Analysis bug] | OLTS Application | 2 | Completed | Jobs was not opened for temp users.
21 | 2018-08-13 | INC000007415989 has been submitted. FR OLTS / Contractor cannot reach timesheets [Change code] | OLTS Application | 3 | Completed
22 | 2018-08-13 | INC000007415989 has been submitted. FR OLTS / Contractor cannot reach timesheets [Unit Testing at development server] | OLTS Application | 1 | Completed
23 | 2018-08-13 | INC000007415989 has been submitted. FR OLTS / Contractor cannot reach timesheets [Testing at PROD environment] | OLTS Application | 0.5 | Completed | Resolved.
24 | 2018-08-13 | Discussing new items of next sprint | OLTS Application | 1.5 | InProgress
25 | 2018-08-14 | Manage URL structure of Authorizer History page [Analysis Workflow] | OLTS Application | 1 | Completed
26 | 2018-08-14 | Manage URL structure of Authorizer History page [Change code] | OLTS Application | 4 | Completed
27 | 2018-08-14 | Manage URL structure of Authorizer History page [Testing] | OLTS Application | 1 | Completed
28 | 2018-08-14 | Discussing new items of next sprint | OLTS Application | 1 | Completed
29 | 2018-08-15 | OFF
30 | 2018-08-16 | #71639 Indicate the dates of the weeks and match them to the calendar [ Analysis Wokflow of code and database] | OLTS Application | 2 | Completed
31 | 2018-08-16 | #71639 Indicate the dates of the weeks and match them to the calendar [Create database script for week number] | OLTS Application | 6 | InProgress
32 | 2018-08-17 | #71639 Indicate the dates of the weeks and match them to the calendar [Create database script for week number] | OLTS Application | 3 | Completed
33 | 2018-08-17 | #71639 Indicate the dates of the weeks and match them to the calendar [Change at code level] | OLTS Application | 4 | Completed | Development done
34 | 2018-08-17 | #71639 Indicate the dates of the weeks and match them to the calendar [Testing at development end] | OLTS Application | 1 | Completed | Testing done
35 | 2018-08-20 | #71632 Simplify the way of creating timesheets each month [ Discussing the workflow for creating timesheet with Vikash] | OLTS Application | 1 | Completed
36 | 2018-08-20 | #71632 Simplify the way of creating timesheets each month [ Analysis the Database script] | OLTS Application | 2 | Completed
37 | 2018-08-20 | #71632 Simplify the way of creating timesheets each month [ Change in Database script] | OLTS Application | 5 | Completed | No changes in code.
38 | 2018-08-21 | #71632 Simplify the way of creating timesheets each month [ Testing with All users] | OLTS Application | 2 | Completed | Testing done
39 | 2018-08-21 | #71627 Email sending to users directly from OLTS [ Discussed the current workflow with vikash] | OLTS Application | 1 | Completed
40 | 2018-08-21 | #71627 Email sending to users directly from OLTS [ Analysis the workflow] | OLTS Application | 1 | Completed
41 | 2018-08-21 | #71627 Email sending to users directly from OLTS [ Create User Interface] | OLTS Application | 4 | InProgress
42 | 2018-08-22 | #71627 Email sending to users directly from OLTS [Create User Interface] | OLTS Application | 4 | InProgress
43 | 2018-08-22 | #71627 Email sending to users directly from OLTS [Change code] | OLTS Application | 4 | InProgress
44 | 2018-08-23 | #71627 Email sending to users directly from OLTS [Create User Interface] | OLTS Application | 6 | InProgress
45 | 2018-08-23 | #71627 Email sending to users directly from OLTS [Create User Interface - Discussion with Anand] | OLTS Application | 1 | InProgress
46 | 2018-08-23 | #71627 Email sending to users directly from OLTS [Create User Interface - Discussion with Vikash] | OLTS Application | 1 | InProgress
47 | 2018-08-24 | #71627 Email sending to users directly from OLTS [Create User Interface] | OLTS Application | 8 | InProgress
48 | 2018-08-27 | #71627 Email sending to users directly from OLTS [Changes at development end for user control] | OLTS Application | 3 | InProgress
49 | 2018-08-27 | #71627 Email sending to users directly from OLTS [Changes in user interface] | OLTS Application | 4 | InProgress
50 | 2018-08-27 | #71627 Email sending to users directly from OLTS [Analysis for database script] | OLTS Application | 1 | InProgress
51 | 2018-08-28 | #71627 Email sending to users directly from OLTS [Create new database script for All users] | OLTS Application | 5 | InProgress
52 | 2018-08-28 | #71627 Email sending to users directly from OLTS [Changes in code behind file to pass parameter to database script] | OLTS Application | 3 | InProgress
53 | 2018-08-29 | #71627 Email sending to users directly from OLTS [Create new database script for All users] | OLTS Application | 3 | InProgress
54 | 2018-08-29 | #71627 Email sending to users directly from OLTS [Changes in code behind file to pass parameter to database script] | OLTS Application | 5 | InProgress
55 | 2018-08-29 | INC000007508270 has been submitted. FR OLTS / Temp Worker change statut [Analysis Issue] | OLTS Application | 0.5 | Completed
56 | 2018-08-29 | INC000007508270 has been submitted. FR OLTS / Temp Worker change statut [Change Status in database] | OLTS Application | 0.5 | Completed
57 | 2018-08-30 | #71627 Email sending to users directly from OLTS [Create new database table for Email Notice Template] | OLTS Application | 1 | Completed
58 | 2018-08-30 | #71627 Email sending to users directly from OLTS [Changes in code behind file to pass parameter to database script] | OLTS Application | 3 | InProgress
59 | 2018-08-30 | #71627 Email sending to users directly from OLTS [Change Code in backend] | OLTS Application | 4 | Completed
60 | 2018-08-31 | #71627 Email sending to users directly from OLTS [Change Code in backend] | OLTS Application | 8 | Completed
61
62
63
64
65
66
67
68
69
70
71
| Date | Task | Project | Effort Hrs | Status | Remarks
| 2018-08-29 | #71627 Email sending to users directly from OLTS [Create new database script for All users] | OLTS Application | 3 | InProgress
| 2018-08-29 | #71627 Email sending to users directly from OLTS [Changes in code behind file to pass parameter to database script] | OLTS Application | 5 | InProgress
| 2018-08-29 | INC000007508270 has been submitted. FR OLTS / Temp Worker change statut [Analysis Issue] | OLTS Application | 0.5 | Completed
| 2018-08-29 | INC000007508270 has been submitted. FR OLTS / Temp Worker change statut [Change Status in database] | OLTS Application | 0.5 | Completed
| 2018-08-30 | #71627 Email sending to users directly from OLTS [Create new database table for Email Notice Template] | OLTS Application | 1 | Completed
| 2018-08-30 | #71627 Email sending to users directly from OLTS [Changes in code behind file to pass parameter to database script] | OLTS Application | 3 | InProgress
| 2018-08-30 | #71627 Email sending to users directly from OLTS [Change Code in backend] | OLTS Application | 4 | Completed

## MSR_August_2018
Bugs of OLTS & OLTS MI ApplicationAugust 2018
Priority | Issue ID | Summary | Task Type | Status | Sprint No | Remarks
|  | Delete timesheet data from database as reported by Business | Bug | Resolved
|  | Timesheet Open Problem | Bug | Resolved
| INC000007415989 | FR OLTS / Contractor cannot reach timesheets | Bug | Resolved
| INC000007508270 | FR OLTS / Temp Worker change statut | Bug | Resolved |  | Change Status in backend
Testing OLTS & OLTS on PRE-PROD & PROD environment August 2018
Priority | Issue ID | Summary | Task Type | Status | Sprint No
|  | Test application on PRE-PROD environment | Testing | Done | Sprint 35
|  | Test application on PROD environment | Testing | Done | Sprint 35
1) New Development of OLTS Application (Sprint 36) (August 18)
Priority | Request ID | Summary | Status | Parent ID | Remarks
3-Low | #71632 | Simplify the way of creating timesheets each month | Done
|  | Changes in Database script for modify timesheets by dates | Done | #71632
3-Low | #71639 | Indicate the dates of the weeks and match them to the calendar | Done
|  | Create new database script for week number | Done | #71639
|  | Changes in Database script for add week number | Done | #71639
3-Low | #72528 | Email address not recognized by the system | Done
3-Low | #72588 | Add the button "Clear" at the new option admin log as user | Done
|  | Give Access to super admin to clear all data. | Done | #72588
3-Low | #71627 | Email sending to users directly from OLTS | InProgress |  | This item will be moved to next sprint
|  | Create New database script for Email Sending | Done | #71627
|  | Create new Database table for newly created email. | Done | #71627
|  | Create new database procedure to fetch all data of email type | Done | #71627
|  | Create new database procedure to fetch all email of users based on selection. | Done | #71627
|  | Create New page for Manage Email Sending | InProgress | #71627
|  | Create New page for Edit Manage Email Sending | InProgress | #71627
|  | Create Script for contractor to view all active contracts | Done |  | July's pending task
|  | Access for Consultant/Super Admin/Admin to View Timesheet | Done
|  | Change Database script for Timesheet status is blank in Find Job Page for Admin. | Done
|  | Manage URL structure of Authorizer History page | Done
Defects Reported by Business August 18
Priority | Issue ID | Summary | Status
|  | Notification service workflow analysis | InProgress
|  | Procedures optimization | InProgress

## Sheet1
Sprint 36 DB Procedure Changes
Is New Procedure | Org Name | Test Name | New Name |  | Backup name
Yes | uspVOTSUpdateEmailNoticeTemplate | uspVOTSUpdateEmailNoticeTemplate | uspVOTSUpdateEmailNoticeTemplate
Yes | uspGetEmailForNotice | uspGetEmailForNotice | uspGetEmailForNotice
Yes | uspGetEmailForAllUser | uspGetEmailForAllUser | uspGetEmailForAllUser
No | uspEvoliaGetActiveContractDetailsForTemp | uspEvoliaGetActiveContractDetailsForTemp_17082018 | uspEvoliaGetActiveContractDetailsForTemp
uspFindWeekNumberWithMonthYear
getweekdetail
| uspFindTSWeeklyStatus | uspFindTSWeeklyStatus_16082018 |  | done on pre prod | uspFindTSWeeklyStatus_BAK_04092018
| uspVOTSGetTempTimesheet | uspVOTSGetTempTimesheet_30072018 | uspVOTSGetTempTimesheet | done on pre prod | uspVOTSGetTempTimesheet_BAK_04092018
| uspVOTSEvoliaFindJobByPKey | uspVOTSEvoliaFindJobByPKey_New |  | No change