## PA_July_2018
Priority | Issue ID | Summary
3-Low | #69824 | Notification management in the section "Manage emails"
1-High | #69792 | Raise the frequency of the sync service and modify hours
1-High | #69424 | Replication of Evolia DB
1-High | #69084 | Same abilities than validators and temp workers as administrator
1-High | #69083 | Maintenance message managed by administrators
3-Low | #69081 | Timesheets visualisation for all users
1-High | #67474 | Admin log as action
1-High | #67472 | Log user route : pages and actions
1-High | #67471 | Create different error message

## DSR_July_2018
Daily Status Report -- July 2018
Name | Deepak Gogia | Manager | Mr. Ravi Singh | Client Name | Hays Business Solution
Employee ID | 1537513 | Email ID | ravi5.s@tcs.com | Location | Noida
Role | Developer | Contact No | 7668401200 | Email ID | deepak.gogia@hays.com
Contact No | 9643439385
Srno | Date | Task | Project | Effort Hrs | Status | Remarks
1 | 2018-07-02 | #69824 Notification management in the section "Manage emails"[Analysis Last Email Send code and changes] | OLTS Application | 2 | On Hold | Collation problem occurred [Need to discuss with Vikash and set status to hold till wednesday]
2 | 2018-07-02 | #69824 Notification management in the section "Manage emails"[Create column in Database and test] | OLTS Application | 2 | Completed
3 | 2018-07-02 | #67472 Log user route : pages and actions [Understanding requiement and current flow] | OLTS Application | 1 | InProgress
4 | 2018-07-02 | OAT environment is not working [ Analysis Bug] | OLTS Application | 1 | InProgress | As discussed with Vikash, this task will resolved by pankaj
5 | 2018-07-02 | #67472 Log user route : pages and actions [Create new web form ] | OLTS Application | 0.5 | InProgress
6 | 2018-07-02 | INC000007160994 Timesheet authorisations pending | OLTS Application | 1.5 | InProgress
7 | 2018-07-03 | INC000007160994 Timesheet authorisations pending | OLTS Application | 4 | Temporary Resolved | Temporary Resolved by pankaj
8 | 2018-07-03 | Timesheet Validated Problem regarding changing month [Analysis problem and Change Code] | OLTS Application | 2 | On Hold | Status set to hold due to Approval pending from vikash
9 | 2018-07-03 | Timesheet Validated Problem regarding changing month [Testing at development end] | OLTS Application | 0.5 | Completed
10 | 2018-07-03 | #67472 Log user route : pages and actions [Create new web form ] | OLTS Application | 1.5 | InProgress | UI Design done
11 | 2018-07-04 | #67472 Log user route : pages and actions [Code Change ] | OLTS Application | 6 | InProgress
12 | 2018-07-04 | INC000007160994 Timesheet authorisations pending [KT by Vikash] | OLTS Application | 1 | Completed
13 | 2018-07-04 | #69824 Notification management in the section "Manage emails"[Analysis and Discussion with Vikash for further development] | OLTS Application | 1 | InProgress
14 | 2018-07-05 | #67472 Log user route : pages and actions [Code Change on Business Layer ] | OLTS Application | 5 | InProgress
15 | 2018-07-05 | #67472 Log user route : pages and actions [Testing of new Development ] | OLTS Application | 0.5 | Completed
16 | 2018-07-05 | #69824 Notification management in the section "Manage emails"[Work on Data Access Layer] | OLTS Application | 2.5 | InProgress
17 | 2018-07-06 | Failed synchronization process | OLTS Application | 1 | Completed | Search invalid Email address and delete it for 2 users.
18 | 2018-07-06 | Understanding Timesheet Approval/Rejection process | OLTS Application | 2 | Completed | for check rejection/approval status
19 | 2018-07-06 | Understanding Timesheet Approval/Rejection process [ Code change for Super Admin] | OLTS Application | 4 | Completed | Enabled Timesheet whose status is created/rejected for Super Admin. Super Admin can fill timesheet and Save time sheet.
20 | 2018-07-06 | Understanding Timesheet Approval/Rejection process [ Testing for All User] | OLTS Application | 1 | Completed
21 | 2018-07-09 | #69824 Notification management in the section "Manage emails"[Change code for Filtering and sorting] | OLTS Application | 2 | Completed | Development done.
22 | 2018-07-09 | #69824 Notification management in the section "Manage emails"[Testing with all users] | OLTS Application | 1 | Completed | #69824 Resolved.
23 | 2018-07-09 | #67472 Log user route : pages and actions [Add code for Validation] | OLTS Application | 4 | Completed | Development done.
24 | 2018-07-09 | #67472 Log user route : pages and actions [Analysis the bug and test it] | OLTS Application | 1 | InProgress
25 | 2018-07-10 | #67472 Log user route : pages and actions [Changes in Stored Procedures] | OLTS Application | 2 | Completed
26 | 2018-07-10 | Analysis the workflow of OLTSWinservices Application | OLTS WinservicesApplication | 4 | InProgress
27 | 2018-07-10 | INC000007211629 FR OLTS / Hourr type "RTT" are not transmitted to Evolia[ Trying to Replicate issue] | OLTS Application | 2 | InProgress
28 | 2018-07-11 | #69824 Notification management in the section "Manage emails"[fix bug for Edit Email Template] | OLTS Application | 6 | Completed
29 | 2018-07-11 | Page Redirect to Login for[Save,Close] Edit Email Template Section | OLTS Application | 2 | InProgress
30 | 2018-07-12 | INC000007226529 Timesheet wrong end date and mismatch about the type[Analysis bug and trying to replicate] | OLTS Application | 2 | Completed
31 | 2018-07-12 | INC000007226529 Timesheet wrong end date and mismatch about the type[Update in OLTS Database] | OLTS Application | 0.5 | Completed
32 | 2018-07-12 | Timesheet Validated Problem regarding changing month [Change Code with Vikash] | OLTS Application | 2.5 | InProgress
33 | 2018-07-12 | Analysis Stored procedure [ for customized] | OLTS Application | 3 | InProgress
34 | 2018-07-13 | Timesheet Validated Problem regarding changing month [Change Code] | OLTS Application | 3 | InProgress
35 | 2018-07-13 | Analysis Stored procedure [ for customized] | OLTS Application | 0.5 | On Hold | Status set to hold due to low priority
36 | 2018-07-13 | Understanding Timesheet Approval/Rejection process [ print and save features for Super Admin] | OLTS Application | 4.5 | Completed | Print and save features are on wrong page so manage code for these features.
37 | 2018-07-16 | Timesheet Validated Problem regarding changing month [Change Code] | OLTS Application | 7 | InProgress | Timesheet submitted only by temp users
38 | 2018-07-16 | Timesheet Validated Problem regarding changing month [Testing of change code] | OLTS Application | 1 | InProgress
39 | 2018-07-17 | Timesheet Validated Problem regarding changing month [Change Code for Timesheet history page and new timesheet] | OLTS Application | 5 | InProgress | Timesheet Validated only for temp users
40 | 2018-07-17 | Timesheet Validated Problem regarding changing month [Testing of change code] | OLTS Application | 3 | InProgress
41 | 2018-07-18 | Timesheet Validated Problem regarding changing month [Change Code for Timesheet history page and new timesheet] | OLTS Application | 5 | Completed | Development done.
42 | 2018-07-18 | Timesheet Validated Problem regarding changing month [Testing of change code] | OLTS Application | 2 | Completed
43 | 2018-07-18 | Testing at OAT environment | OLTS Application | 1 | InProgress
44 | 2018-07-19 | Testing at OAT environment | OLTS Application | 6 | InProgress
45 | 2018-07-20 | Analysis Stored procedure [ for customized] | OLTS Application | 0.5 | Completed | Status set to hold due to low priority Status set to complete because there is no need to check this.
46 | 2018-07-20 | Testing at OAT environment | OLTS Application | 5.5 | Completed
47 | 2018-07-20 | Analysis Evolia Database | OLTS Application | 2 | InProgress
48 | 2018-07-23 | Testing at OAT environment | OLTS Application | 1 | Completed
49 | 2018-07-23 | View Timesheet Problem for Admin [Analysis the workflow of find job] | OLTS Application | 1 | Completed
50 | 2018-07-23 | View Timesheet Problem for Admin [Change the Database procedure for find job] | OLTS Application | 3 | Completed
51 | 2018-07-23 | View Timesheet Problem for Admin [Change Code for find job] | OLTS Application | 1 | Completed
52 | 2018-07-23 | View Timesheet Problem for Admin [Testing] | OLTS Application | 1 | Completed
53 | 2018-07-23 | View Timesheet Problem for Admin [CSS properties change] | OLTS Application | 0.5 | Completed
54 | 2018-07-23 | View Timesheet Problem for Admin [Testing of development] | OLTS Application | 0.5 | Completed
55 | 2018-07-24 | Direct Access for different profile [Analysis all user profile cases | OLTS Application | 2 | Completed
56 | 2018-07-24 | Direct Access for different profile [Development for direct access for all user] | OLTS Application | 4.5 | Completed
57 | 2018-07-24 | Direct Access for different profile [Testing of new development along with previous cases] | OLTS Application | 1.5 | Completed
58 | 2018-07-25 | Create Script for running contractor [Analysis Database structure] | OLTS Application | 1.5 | Completed
59 | 2018-07-25 | Create Script for running contractor [Create Database procedure] | OLTS Application | 5 | InProgress
60 | 2018-07-25 | Direct Access for different profile [Testing of new development with live configuration] | OLTS Application | 1.5 | Completed
61 | 2018-07-27 | #71571 Visualisation of previous months [ Analysis the current flow] | OLTS Application | 2 | Completed
62 | 2018-07-27 | #71571 Visualisation of previous months [ Change in code with Vikash] | OLTS Application | 5 | Completed
63 | 2018-07-27 | #71571 Visualisation of previous months [Testing of code] | OLTS Application | 1 | Completed
64 | 2018-07-30 | Hours cannot save after reset in timesheet [Analysis the process of temp user] | OLTS Application | 3 | Completed
65 | 2018-07-30 | Hours cannot save after reset in timesheet [Code change for temp user] | OLTS Application | 5 | Completed | Development has been applied on Test environment
66 | 2018-07-31 | Hours cannot save after reset in timesheet [Create test cases forr temp user] | OLTS Application | 1 | Completed
67 | 2018-07-31 | Hours cannot save after reset in timesheet [Code change for history page for temp user] | OLTS Application | 6 | Completed | Not applied on Test environment
68 | 2018-07-31 | Hours cannot save after reset in timesheet [Test history page for temp user] | OLTS Application | 1 | Completed
| Date | Task | Project | Effort Hrs | Status | Remarks

## MSR_July_2018
Bugs of OLTS & OLTS MI Application July 2018
Priority | Issue ID | Summary | Task Type | Status | Sprint No | Remarks
|  | Timesheet Validated Problem regarding changing month | Bug | Resolved | Sprint 35 | Resolved but not deploy on LIVE environment
|  | Failed synchronization process | Bug | Resolved | Sprint 35 | Search invalid Email address and delete it for 2 users.
|  | Page Redirect to Login for[Save,Close] Edit Email Template Section | Bug | Resolved
| INC000007226529 | Timesheet wrong end date and mismatch about the type | Bug | Resolved | Sprint 35 | Update in OLTS Database
| #71571 | Visualisation of previous months | Bug | Resolved
|  | Hours cannot save after reset in timesheet | Bug | Resolved
Configure OLTS & OLTS MI Application on PRE-PROD & PROD environment July 2018
Priority | Issue ID | Summary | Task Type | Status | Sprint No
1-High |  | Configured application on PRE-PROD environment | Testing | Done | Sprint 35
1) New Development of OLTS Application (Sprint 35) (July 18)
Priority | Issue ID | Summary | Status
3-Low | #69824 | Notification management in the section "Manage emails" | Done
1-High | #69083 | Maintenance message managed by administrators | Done
3-Low | #69081 | Timesheets visualisation for all users | Fix not required
1-High | #67474 | Admin log as action | Done
1-High | #67472 | Log user route : pages and actions | Done
|  | Create Stored procedures to find LastEmailSent in OLTS Database | Done
|  | Create database script for tracking report in OLTS Database | Done
|  | Add Validation in Manage Emails section | Done
|  | Give Timesheet "Save" permission to super admin | Done
|  | Enable print features for Super Admin | Done
|  | Change Url structure for New timesheet page | Done
|  | Navigate All timesheet pages to one standard Url structure | Done
|  | Change database script to View Timesheet from "find job" section for super admin | Done
|  | Enable/Disable timesheet button or color code to View Timesheet from "find job" section for super admin | Done
|  | Direct Access for different profile | Done
|  | Create Script for contractor to view all active contracts | InProgress
|  | Timesheet Status is blank in Find Job Page for admin | Done
|  | Month changing for Timesheet history page | Done

## Sheet1
New Development OLTS & OLTS MI Application July 2018
Priority | Issue ID | Summary | Task Type | Status | Sprint No
3-Low | #69824 | Notification management in the section "Manage emails" | New Dev | Done | Sprint 35 |  | #69824
1-High | #69792 | Raise the frequency of the sync service and modify hours | New Dev | Pending | Sprint 35 |  | #69083
1-High | #69424 | Replication of Evolia DB | New Dev | Pending | Sprint 35 |  | #69081
1-High | #69084 | Same abilities than validators and temp workers as administrator | New Dev | Pending | Sprint 35 |  | #67474
1-High | #69083 | Maintenance message managed by administrators | New Dev | Pending | Sprint 35 |  | #67472
3-Low | #69081 | Timesheets visualisation for all users | New Dev | Done | Sprint 35 | save by super admin
1-High | #67474 | Admin log as action | New Dev | Pending | Sprint 35
1-High | #67472 | Log user route : pages and actions | New Dev | Done | Sprint 35
1-High | #67471 | Create different error message | New Dev | Pending | Sprint 35
Bugs of OLTS & OLTS MI Application July 2018
Priority | Issue ID | Summary | Task Type | Status | Sprint No | Remarks
1-High |  | OAT environment is not working | Bug | Pending | Sprint 35 | Resolved by Vikash
| INC000007160994 | INC000007160994 Timesheet authorisations pending | Bug | Resolved | Sprint 35 | Temporary Resolved by pankaj 030718
|  | Timesheet Validated Problem regarding changing month | Bug | Resolved | Sprint 35 | Resolved but not deploy on LIVE environment
|  | Failed synchronization process | Bug | Resolved | Sprint 35 | Search invalid Email address and delete it for 2 users.
| INC000007211629 | FR OLTS / Hourr type "RTT" are not transmitted to Evolia | Bug | Done |  | At evolia end
Configure OLTS & OLTS MI Application on OAT & PROD environment July 2018
Priority | Issue ID | Summary | Task Type | Status | Sprint No
1-High |  | Configured application on OAT environment | Testing | Done | Sprint 35
1-High |  | Configured application on PROD environment | Live | Done | Sprint 35
1) New Development of OLTS Application (Sprint 35)
Priority | Issue ID | Summary | Task Type | Status | Sprint No
3-Low | #69824 | Notification management in the section "Manage emails" | New Dev | Done | Sprint 35
1-High | #69083 | Maintenance message managed by administrators | New Dev | Done | Sprint 35
3-Low | #69081 | Timesheets visualisation for all users | New Dev | Done | Sprint 35
1-High | #67474 | Admin log as action | New Dev | Done | Sprint 35
1-High | #67472 | Log user route : pages and actions | New Dev | Done | Sprint 35