## DSR_June_2018
Daily Status Report -- June 2018
Name | Deepak Gogia | Manager | Mr. Ravi Singh | Client Name | Hays Business Solution
Employee ID | 1537513 | Email ID | ravi5.s@tcs.com | Location | Noida
Role | Developer | Contact No | 7668401200 | Email ID | deepak.gogia@hays.com
Contact No | 9643439385
Srno | Date | Task | Project | Effort Hrs | Status | Remarks
1 | 2018-06-01 | #69606 Temp Wip - Report and Back Office to hide [understand the workflow] | OLTS MI Application | 1 | Completed
2 |  | #69606 Temp Wip - Report and Back Office to hide [develop changes] |  | 4 | Completed
3 | 2018-06-01 | Issue related to Observer | OLTS Application | 3 | Completed | Email Process is ok we have to checked this in Evolia End. [Informed to Vikash]
4 | 2018-06-04 | #69606 Temp Wip - Report and Back Office to hide [Testing of new development] | OLTS MI Application | 4 | Completed
5 | 2018-06-04 | #68499 Section "Opened Contract" is empty [ Code change related to All users | OLTS Application | 4 | InProgress | Development done for Super user and Administrator.
6 | 2018-06-05 | #68499 Section "Opened Contract" is empty [ Code change related to All users | OLTS Application | 4 | Completed | #68499 Section "Opened Contract" is empty development task done
7 | 2018-06-05 | #68499 Section "Opened Contract" is empty [ Testing of new development with old development] | OLTS Application | 4 | Completed
8 | 2018-06-06 | #69603 OLTS MI - Temp details documents to hide [Analysis Workflow for Temp WIZ] | OLTS MI Application | 6 | Completed
9 | 2018-06-06 | #69603 OLTS MI - Temp details documents to hide [Testing Previous Development for Temp WIZ] | OLTS MI Application | 2 | Completed
10 | 2018-06-07 | #69603 OLTS MI - Temp details documents to hide [Change Code for Contract Detail] | OLTS MI Application | 6 | Completed
11 | 2018-06-07 | #69603 OLTS MI - Temp details documents to hide [Testing for Contract Detail] | OLTS MI Application | 2 | Completed
12 | 2018-06-08 | #69603 OLTS MI - Temp details documents to hide [Analysis flow for Payment Detail with Vikash] | OLTS MI Application | 5 | Completed
13 | 2018-06-08 | Bug Occurred on live[ Analysis Error] | OLTS Application | 3 | InProgress | Object cannot be cast from DBNull to other types.
14 | 2018-06-11 | Bug Occurred on live [Resolving error] | OLTS Application | 6 | InProgress
15 | 2018-06-11 | #69603 OLTS MI - Temp details documents to hide [Code change for Payment Detail with Vikash] | OLTS MI Application | 2 | InProgress
16 | 2018-06-12 | Bug Occurred on live [Code Change with Vikash] | OLTS Application | 4 | Completed | Object cannot be cast from DBNull to other types. -- Bug Resolved
17 | 2018-06-25 | Validate timesheet at submission[Analysis the current workflow of code] | OLTS Application | 1.5 | Completed
18 | 2018-06-25 | Validate timesheet at submission [Analysis the previous test cases] |  | 1 | Completed
19 | 2018-06-25 | Validate timesheet at submission [Analysis the code change] Timesheet should be validated for created and rejected status. |  | 5.5 | Completed
20 | 2018-06-26 | Validate timesheet at submission [Create new test cases and test with old functionality as well] | OLTS Application | 3 | Completed
21 | 2018-06-26 | Configuring OTLS MI on PROD environment [Sprint 34] Analysis Prod Environment with Vikash | OLTS MI Application | 1 | Completed
22 | 2018-06-26 | Configuring OTLS on PROD environment [Sprint 34] Analysis Prod Environment with Vikash | OLTS Application | 1 | Completed
23 | 2018-06-26 | Configuring OTLS MI on PROD environment [Sprint 34] Analysis Prod Environment with Vikash | OLTS MI Application | 1.5 | Completed
24 | 2018-06-26 | Configuring OTLS on PROD environment [Sprint 34] Analysis Prod Environment with Vikash | OLTS Application | 1.5 | Completed
25 | 2018-06-27 | Configured OTLS on PROD environment [Sprint 34] | OLTS Application | 0.5 | Completed
26 | 2018-06-27 | Configured OTLS MI on PROD environment [Sprint 34] | OLTS MI Application | 0.5 | Completed
27 | 2018-06-27 | Configured OTLS on PROD environment [Sprint 34] Test all changes in sprint 34 with vikash | OLTS Application | 0.5 | Completed
28 | 2018-06-27 | Configuring OTLS MI on PROD environment [Sprint 34] Test all changes in sprint 34 with vikash | OLTS MI Application | 0.5 | Completed
29 | 2018-06-27 | Validate timesheet at submission [Analysis the code change with Vikash] | OLTS Application | 6 | Completed
30 | 2018-06-28 | Test OTLS MI on Prod environment | OLTS MI Application | 1 | Completed
31 | 2018-06-28 | Validate timesheet at submission [Test all changes with Vikash] | OLTS Application | 3 | Completed
32 | 2018-06-28 | Validate timesheet at submission [Resolve all Bugs with Vikash] | OLTS Application | 4 | Completed
33 | 2018-06-29 | #69824 Notification management in the section "Manage emails"[Analysis Email Frequency Code and changes] | OLTS Application | 3 | Completed
34 | 2018-06-29 | #69824 Notification management in the section "Manage emails"[Analysis Last Email Send code and changes] | OLTS Application | 2 | InProgress
35 | 2018-06-26 | Sports Day |  | 3

## MSR_June_2018
New Development OLTS & OLTS MI Application June 2018
Priority | Issue ID | Summary | Task Type | Status | Sprint No
1-High | #69606 | Temp Wip - Report and Back Office to hide | New Dev | Done | Sprint 34
1-High | #69603 | OLTS MI - Temp details documents to hide | New Dev | Done | Sprint 34
1-High | #69079 | Temp Wip - empty fields | New Dev | Done | Sprint 34
2-Medium | #68499 | Section "Opened Contract" is empty | New Dev | Done | Sprint 34
Bugs of OLTS & OLTS MI Application June 2018
Priority | Issue ID | Summary | Task Type | Status | Sprint No
1-High |  | Issue related to Observer | Bug | Resolved | Sprint 34
1-High |  | Issue occurred in submission of timesheet [Type Error] | Bug | Resolved | Sprint 34
1-High |  | Issue occurred in Encryption Decryption | Bug | Resolved | Sprint 34
1-High | #69791 | Hours and days changing on OLTS | Bug | Resolved | Sprint 34
1-High |  | URL not updating on changing month in OLTS | Bug/New Dev | Resolved | Sprint 34
Configure OLTS & OLTS MI Application on OAT & PROD environment June 2018
Priority | Issue ID | Summary | Task Type | Status | Sprint No
1-High |  | Configured application on OAT environment | Testing | Done | Sprint 34
1-High |  | Configured application on PROD environment | Live | Done | Sprint 34