## PA_September_2018
Priority | Issue ID | Summary | Status | Remarks
1-High | #74335 | OLTS MI - Maintain the session active more than 2 minutes | InProgress
1-High | #74331 | OLTS MI - Possibility to apply a filter on the contract lines "On hold" | InProgress
1-High | #73746 | OLTS MI - Stop the sending of notification emails from FM & Amends | InProgress
1-High | #73725 | OLTS MI - Rename the button confirm and modify the associated workflow | InProgress
1-High | #73687 | OLTS MI - Adjustment of the wip view according to the role. | InProgress
3-Low | #71627 | Email sending to users directly from OLTS | OnHold | Moved to next sprint
|  | Create New page for Edit Manage Email Sending | Pending | Moved to next sprint
Defects Reported by Business August-September 18
Priority | Issue ID | Summary | Status
|  | Notification service workflow analysis | InProgress
|  | Procedures optimization | InProgress

## DSR_September_2018
Daily Status Report -- September 2018
Name | Deepak Gogia | Manager | Mr. Ravi Singh | Client Name | Hays Business Solution
Employee ID | 1537513 | Email ID | ravi5.s@tcs.com | Location | Noida
Role | Developer | Contact No | 7668401200 | Email ID | deepak.gogia@hays.com
Contact No | 9643439385
Srno | Date | Task | Project | Effort Hrs | Status | Remarks
1 | 2018-09-03 | #71627 Email sending to users directly from OLTS [Change Code in backend] | OLTS Application | 5 | Completed
2 | 2018-09-03 | #71627 Email sending to users directly from OLTS [Create database script for Save Data from UI] | OLTS Application | 3 | Completed
3 | 2018-09-04 | #71627 Email sending to users directly from OLTS [Create database script for Update Data from UI] | OLTS Application | 3 | Completed
4 | 2018-09-04 | #71627 Email sending to users directly from OLTS [Change code for handle data] | OLTS Application | 4 | InProgress
5 | 2018-09-04 | Discussion with business for next sprint | OLTS & OLTS MI Application | 1 | Completed
6 | 2018-09-05 | INC000007546272 Timesheet sent by mail cannot be submitted [Analysis Email sending process] | OLTS Application | 4 | InProgress
7 | 2018-09-05 | INC000007546272 Timesheet sent by mail cannot be submitted [Create Scenario at development end and test] | OLTS Application | 4 | InProgress
8 | 2018-09-05 | INC000007546272 Timesheet sent by mail cannot be submitted [testing] | OLTS Application | 6 | InProgress
9 | 2018-09-05 | Discussion with business for next sprint with Vikash | OLTS & OLTS MI Application | 2 | Completed
10 | 2018-09-06 | INC000007546272 Timesheet sent by mail cannot be submitted [Change in Code for further test] | OLTS Application | 6 | Completed
11 | 2018-09-06 | INC000007546272 Timesheet sent by mail cannot be submitted [Test at Pre-Prod Environment ] | OLTS Application | 1 | Completed
12 | 2018-09-06 | INC000007546272 Timesheet sent by mail cannot be submitted [Test at Prod Environment ] | OLTS Application | 0.5 | Completed
13 | 2018-09-07 | INC000007546272 Timesheet sent by mail cannot be submitted [Redirect issue occurred-Analysis ] | OLTS Application | 5 | InProgress
14 | 2018-09-07 | INC000007546272 Timesheet sent by mail cannot be submitted [create client side script to resolve issue ] | OLTS Application | 3 | InProgress
15 | 2018-09-10 | INC000007546272 Timesheet sent by mail cannot be submitted [create client side script to resolve issue ] | OLTS Application | 4 | Completed
16 | 2018-09-10 | INC000007546272 Timesheet sent by mail cannot be submitted [Test at Pre-Prod] | OLTS Application | 0.5 | Completed
17 | 2018-09-10 | INC000007546272 Timesheet sent by mail cannot be submitted [Test at Prod] | OLTS Application | 0.5 | Completed
18 | 2018-09-10 | Discussion with business for next sprint | OLTS & OLTS MI Application | 1.5 | Completed
19 | 2018-09-10 | Analysis item of new sprint with Team | OLTS & OLTS MI Application | 1.5 | Completed
20 | 2018-09-11 | Analysis item of new sprint | OLTS & OLTS MI Application | 4 | Completed
21 | 2018-09-11 | #73967] New Issue Assigned: Change the font size[Analysis] | OLTS Application | 0.5 | InProgress
22 | 2018-09-11 | #73967] New Issue Assigned: Change the font size[change code] | OLTS Application | 1 | Completed
23 | 2018-09-11 | #73968] New Issue Assigned: Sort chronologically months [ Analysis] | OLTS Application | 0.5 | Completed
24 | 2018-09-11 | #73968] New Issue Assigned: Sort chronologically months [ Changes in databse script] | OLTS Application | 1 | Completed
25 | 2018-09-11 | INC000007581007 has been submitted. FR OLTS / Validator cannot find timesheet in the history [Analysis record] | OLTS Application | 1 | Completed | Running fine
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
| Date | Task | Project | Effort Hrs | Status | Remarks
| 2018-09-05 | INC000007546272 Timesheet sent by mail cannot be submitted [Analysis Email sending process] | OLTS Application | 4 | InProgress
| 2018-09-05 | INC000007546272 Timesheet sent by mail cannot be submitted [Create Scenario at development end and test] | OLTS Application | 4 | InProgress
| 2018-09-05 | INC000007546272 Timesheet sent by mail cannot be submitted [testing] | OLTS Application | 6 | InProgress
| 2018-09-05 | Discussion with business for next sprint with Vikash | OLTS & OLTS MI Application | 2 | Completed
| 2018-09-06 | INC000007546272 Timesheet sent by mail cannot be submitted [Change in Code for further test] | OLTS Application | 6 | Completed
| 2018-09-06 | INC000007546272 Timesheet sent by mail cannot be submitted [Test at Pre-Prod Environment ] | OLTS Application | 1 | Completed
| 2018-09-06 | INC000007546272 Timesheet sent by mail cannot be submitted [Test at Prod Environment ] | OLTS Application | 0.5 | Completed
| 2018-09-07 | INC000007546272 Timesheet sent by mail cannot be submitted [Redirect issue occurred-Analysis ] | OLTS Application | 5 | InProgress
| 2018-09-07 | INC000007546272 Timesheet sent by mail cannot be submitted [create client side script to resolve issue ] | OLTS Application | 3 | InProgress
| 2018-09-10 | INC000007546272 Timesheet sent by mail cannot be submitted [create client side script to resolve issue ] | OLTS Application | 4 | Completed
| 2018-09-10 | INC000007546272 Timesheet sent by mail cannot be submitted [Test at Pre-Prod] | OLTS Application | 0.5 | Completed
| 2018-09-10 | INC000007546272 Timesheet sent by mail cannot be submitted [Test at Prod] | OLTS Application | 0.5 | Completed
| 2018-09-10 | Discussion with business for next sprint | OLTS & OLTS MI Application | 1.5 | Completed
| 2018-09-10 | Analysis item of new sprint with Team | OLTS & OLTS MI Application | 1.5 | Completed
| 2018-09-11 | Analysis item of new sprint | OLTS & OLTS MI Application | 4 | Completed
| 2018-09-11 | #73967] New Issue Assigned: Change the font size[Analysis] | OLTS Application | 0.5 | InProgress
| 2018-09-11 | #73967] New Issue Assigned: Change the font size[change code] | OLTS Application | 1 | Completed
| 2018-09-11 | #73968] New Issue Assigned: Sort chronologically months [ Analysis] | OLTS Application | 0.5 | Completed
| 2018-09-11 | #73968] New Issue Assigned: Sort chronologically months [ Changes in databse script] | OLTS Application | 1 | Completed
| 2018-09-11 | INC000007581007 has been submitted. FR OLTS / Validator cannot find timesheet in the history [Analysis record] | OLTS Application | 1 | Completed | Running fine

## MSR_September_2018
Bugs of OLTS & OLTS MI Application September 2018
Priority | Issue ID | Summary | Task Type | Status | Sprint No | Remarks
| INC000007546272 | Timesheet sent by mail cannot be submitted | Bug | Resolved |  | Changes in Js file.
| INC000007581007 | Validator cannot find timesheet in the history | Bug | Resolved |  | Validator name has been changed
| #73967 | Change the font size | Bug | Resolved | Sprint 36 | changes in DB script as well as code.
| #73968 | Sort chronologically months | Bug | Resolved | Sprint 36 | changes in DB script
| INC000007592454 | Hours disappearing from OLTS but still into Evolia | Bug | Resolved
| INC000007609772 | Week NA while contract running | Bug | Resolved
| INC000007632121 | OLTS MI / Access to the section TF & Amends | Bug | Resolved
| INC000007643307 | OLTS / Wrong display | Bug | Resolved
| INC000007662352 | OLTS / Real end date week is NA status | Bug | Resolved
| INC000007663876 | OLTS / Modification of the validator's | Bug | Resolved
1) New Development of OLTS Application (Sprint 37) (September 18)
Priority | Issue ID | Summary | Status | Parent ID | Remarks
1-High | #73725 | OLTS MI - Rename the button confirm and modify the associated workflow | Done
|  | Rename the button to Send BO TT and save data into database | Done
|  | Changes in Database script to modify contract | Done
|  | Stop sending of email sercvice through Manager/Consultant. | Done
|  | Add some validation before sending email | Done
1-High | #73687 | OLTS MI - Adjustment of the wip view according to the role. | Done
|  | Create new users (HelpTT users) in XML file and definded their role. | Done | #73687
|  | Changes in DB scripting for analysis user type and their requirement | Done | #73687
|  | Changes in js file to manage wip view. | Done | #73687
1-High | #74331 | OLTS MI - Possibility to apply a filter on the contract lines "On hold" | Done
|  | Add DB scripts to Update Hold values. | Done | #74331
|  | Changes in Database script to identify user performed task. | Done | #74331
|  | Modify database table structure to identify user performed task | Done | #74331
|  | Modify User interface for different users | Done | #74331
|  | Add batch sending procedure for selected user | Done | #74331
|  | Stop Email sending procedure from different users | Done | #74331
|  | Add filter on contract | InProgress | #74331
1-High | #74335 | OLTS MI - Maintain the session active more than 2 minutes | InProgress
1-High | #73746 | OLTS MI - Stop the sending of notification emails from FM & Amends | InProgress
Configure OLTS & OLTS MI Application on PRE-PROD & PROD environment September 2018
Priority | Issue ID | Summary | Task Type | Status | Sprint No
1-High |  | Configured application on PRE-PROD environment | Testing | Done | Sprint 36
Defects Reported by Business August-October 18
Priority | Issue ID | Summary | Status
|  | Notification service workflow analysis | InProgress
|  | Procedures optimization | InProgress
Priority | Issue ID | Summary | Status | Parent ID | Remarks
1-High | #74335 | OLTS MI - Maintain the session active more than 2 minutes | InProgress
1-High | #73746 | OLTS MI - Stop the sending of notification emails from FM & Amends | InProgress

## Sheet1
1 | 31 | 31 01-05/08
2 | 32 | 32 06-12/08
3 | 33 | 33 13-19/08
4 | 34 | 34 20-26/08
5 | 35 | 35 27-31/08